Community Services action plan v0.5

Mid July – Mid September

| What are we doing | Target Audience | Where are we doing it | Activities involved | How | Project Owner | Who | Delivery Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Post consultation Activities | ICCT | Community Team Bases | Workstreams: Roles and Responsibilities IT Training and Development | Task and Finish group | Janet Brennan | JB / MC / PB | Mid Sept |
| Briefing out to GP’s and practice managers | Primary Care | N/A | Letter to practices with action plan | What has been done to date Ideas for involvement What can we do for you? | RK/ Dr AB | RK | 18 Sep 15 |
| Individual team briefings | ICNS |  | Team Briefings | Team Briefings | PC | Service Leads | Mid Sept |
| Individual team briefings | ICRS |  | Team Briefings | Team Briefings | PC | Service Leads | Mid Sept |
| Individual team briefings | MSK, Rheumatology & Pain |  | Team Briefings | Team Briefings | PC | Service Leads | Mid Sept |
| Design Comms materials | Staff Primary Care CCG MCC MMHSCT Patients ? | N/A | Describe new services available | Posters – month of activities Leaflets Briefing pack for deliverer Presentations | PC | PB / AH | 18 Sep 15 |
| Update at Meeting | Provider partnership | N/A | Engagement throughout | Information sharing | PC | RK / S Baxter | Fortnightly meetings |

W/c 14 September 2015 	Pre-engagement events

| What are we doing | Target Audience | Where are we doing it | Activities involved | How | Project Owner | Who | Delivery Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Inform staff of changes to Community Services | All UHSM staff | Wythenshawe hospital | Leaders forum | Regular Meeting 1st Sep or 13th Oct | PB to email AMM (Comms) | RK | 13 Oct 15 |
|  |  | N/A | UHSM Life | Article in Magazine | PB | UHSM Comms/PB | Oct Edition |
|  |  | All UHSM locations | Daily UHSM Updates | Screen message when systems accessed. Copy needs to go thru Helen Carruthers in Medical Illustrations. There will be a small charge | PB | PB UHSM Comms Helen Carruthers | Early Sept |
| CEO Blog | All UHSM staff | System based UHSM Update | Article | System Message | PC | AMM | w/c 21 Sept 15 |
| Briefing to Clinical Directors | Clinical Directors | Meeting Venue - TBC | Presentation to Clincal Directors | Presentation | RK | RK | Mid Sept |
| In depth briefing to teams | A&E / Discharge teams/Wards | Ward managers meeting Urgent Care directorate meeting Discharge team meeting | Specific briefing Urgent care Internal Discharge team | Specific briefing Urgent care Internal Discharge team | PB/JW | Clinical Leads SB VI/GP/CR S Boag | w/c 14 Sept 15 |
| CCG Event | GP Practices | TBC | Question and Answer session | Speak to Jayne Fowler | PC |  | 09 Oct 15 |

W/c 21 September 2015 	GP Awareness Week

| What are we doing | Target Audience | Where are we doing it | Activities involved | How | Project Owner | Who | Delivery Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ‘One Team’ GP lead engagement | Dr A B | Practice | Full specification briefing | Meeting | PC | PC | 25 Aug 15 |
| Practice / Patch visits | GP staff teams | As required | Briefing | Briefing | PC | PB /JW /AM to introduce PS | As required |
| Newspaper Column | Patients / residents | Manchester Weekly News | Weekly column | Article | PC | Ann-Marie Miller / Comms | Weekly from 1st Sept 15 |
| Letter to GP’s | GP’s / Primary Care staff | N/A | Letter | Letter | RK | RK | w/c 21 Sept 15 |

UHSM Open Day 27 September 2015

| What are we doing | Target Audience | Where are we doing it | Activities involved | How | Project Owner | Who | Delivery Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Launch Service Specifications | Staff Patients Carers | ERC | Promotional stand Leaflets Posters | Promotional stand Leaflets Posters | PC | Clinical Leads / Teams PB/AH/Therapist/Nurse | 27th Sept 15 |

W/c 29 Sept 2015	 Frailty   (Falls awareness week – 29th Sept 15 and Older Peoples Day 1st Oct)

| What are we doing | Target Audience | Where are we doing it | Activities involved | How | Project Owner | Who | Delivery Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Frailty App | Staff / Carers / Patients | Various locations | Demonstration Complete Frailty App | Promotional stands in various locations | PS | Louise Rogerson - Intelesant | Daily from 29 Sept 15 |
| Falls Awareness | Patients / Carers | TBC | TBC | TBC | PB | TBC | TBC |
| Continence | Patients / Carers | TBC | TBC | TBC | PB | TBC | TBC |
| Exercise Classes (Tai Chi) | Patients | Wellington House | Exercise sessions | Exercise sessions | PB | TBC | TBC |
|  |  | Buccleuch Lodge |  |  |  | Diane Green | TBC |
|  |  | Withington Comm Hosp |  |  |  | TBC | TBC |
| Care and Repair activity TBC | Staff / Patients / Carers | TBC | TBC | TBC | AH | Care and Repair |  |
| Demonstrate community alarm equipment | Staff / Patients / Carers | Various | Advice Leaflets Demonstrations | TBC | RF | Community Alarm Donna Connors |  |
| Assistive technology | Staff / Patients / Carers | Various | Advice Demonstrations | TBC | RF | Independent Life Solutions |  |
| Manchester Carers activity | Carers | TBC | TBC | TBC | RF | Manchester Carers |  |
| Grip Strength tests | Patients | GP Practices | TBC | TBC | PB | GP Practices |  |
| Trips and Falls Smoke Alarms | Staff Patients Carers | TBC | TBC | TBC | RK | C R I T Police / PCSO’s |  |
| Newspaper Column | Patients / residents | Manchester Weekly News | Weekly column | Article | Comms | Ann-Marie Miller / Comms | Weekly from 1st Sept 15 |

W/c 5th October 2015 	Mental Health – (Trish Dwyer?) 0161 882 1000

| What are we doing | Target Audience | Where are we doing it | Activities involved | How | Project Owner | Who | Delivery Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TBC | TBC | Schools / Colleges | TBC | TBC | PC | TD |  |
|  |  | The Forum |  |  |  |  |  |
|  |  | Withington Comm Hosp |  |  |  |  |  |
|  |  | UHSM |  |  |  |  |  |
|  |  | Mental Health Charities |  |  |  |  |  |
| Newspaper Column | Patients / residents | Manchester Weekly News | Weekly column | Article | PC | Ann-Marie Miller / Comms | Weekly from 1st Sept 15 |

W/c 12 October 2015		Living Well in Manchester – Events to raise awareness

| What are we doing | Target Audience | Where are we doing it | Activities involved | How | Project Owner | Who | Delivery Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MSK Event |  |  |  |  | PB | Stephen Boag?? |  |
| Awareness sessions | Patients | Withington Comm Hospital & The Forum? | Blood Pressure awareness | Tests Support Measures Information Advice Ideas | PB | Various |  |
|  |  |  | Alcohol Liaison |  |  |  |  |
|  |  |  | Smoking cessation |  |  |  |  |
|  |  |  | Diabetes |  |  |  |  |
|  |  |  | Nutrition |  |  |  |  |
|  |  |  | Stroke |  |  |  |  |
| Grand Day Out | Residents / patients / Carers | The Forum | various | Weekly event | AH | Jane Ayrton | Wednesdays 10-4pm |
| Tone and trim Exercises | Patients / Carers | Wythenshawe Centre | Exercise | Various | AH | Janice Wilson |  |
| TBC | Age Friendly Manchester | TBC | TBC | TBC | RF | Paul McGarry - MCC |  |
| TBC |  | TBC | TBC | TBC | RF |  |  |
| Coffee and Cake | Residents | Various | Discussions Information | Discussions Information | RK | Good Neighbours |  |
| Classes | Expert Patient | Various | Raising awareness Understanding conditions | Classes | PB | Alicia Lucas Tel : 291 2055 |  |
| Healthy Cooking | Patients / Carers / Residents | Schools / Colleges | TBC | Cooking Classes | PB | Nutrition – Ray Green?? |  |
| Health Awareness | Staff / Patients / Carers | Community Risk Intervention team | Trips and Falls | Fire Service | RF | Falls specialist University of Manchester |  |
|  | Staff / Patients / Carers |  |  | NWAS | RF |  |  |
|  | Staff / Patients / Carers |  |  | Police / PCSO’s | RF |  |  |
| Manchester Carers activity | Carers | TBC | TBC | TBC | RK | Manchester Carers |  |
|  |  |  |  | Community Explorers |  | Claire Tomkinson |  |
| Newspaper Column | Patients / residents | Manchester Weekly News | Weekly column | Article | PC | Ann-Marie Miller / Comms | Weekly from 1st Sept 15 |

W/c 19 October 2015 	General Out of Hospital Community Services

| What are we doing | Target Audience | Where are we doing it | Activities involved | How | Project Owner | Who | Delivery Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Update on Cimmunity Service Offer | Staff / Patients / Carers | Various | Promotional stands Photos and Stories Leaflets / Posters | Promotional Wall – Photos and stories | JW | Clinical Leads |  |
| MSK Gateway | Stephen Boag | TBC | TBC | TBC | TBC | TBC |  |
| Grand Round event |  | ERC Lecture theatre | Presentation to Medical Staff | Presentation to Medical Staff | RK | RK | 23rd Oct 15 |
| You Asked .. We Did. | GP Fed / Practice staff | N/A | Update and Advise on New offer | Letter | RK | RK |  |
| Single Assessment Tool launch | Community Staff | TBC | Care plan creation / Sharing | Launch Single Assessment Tool to carers | Clinical Leads | SB VI/GP/CR S Boag |  |
| How can we improve patient engagement | PPAG | TBC | Service Offer briefing | Meeting | PB to speak to Alicia Lucas | Clinical Leads | TBC |
| Promotional Wall – Photos and stories | Staff / Patients / Students | ERC Foyer | Display Info | Promotional Wall Photos and stories | Repeat of Open Day |  |  |
| Forward view | UHSM Manchester Carers Forum Comm Explorers | Various | Update on what will happen in April 2016 | TBC | Peta Stross? | Comms rep on LLLB Workstream |  |
| Newspaper Column | Patients / residents | Manchester Weekly News | Weekly column | Article | PC | Ann-Marie Miller / Comms | Weekly from 1st Sept 15 |
| Demonstrate community alarm equipment | Staff / Patients / Carers | Various | Advice Leaflets Demonstrations | TBC | RF | Community Alarm Donna Connors |  |

23 October 2015	 Big Event – GP Engagement

| What are we doing | Target Audience | Where are we doing it | Activities involved | How | Project Owner | Who | Delivery Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Educational Session | GP’s | ERC | GP Training Session | GP Training Session | RK/PS/Dr AB | Silas Nichols? Clinical Leads Ray Keelan | TBC Need to confirm with Teresa Gough |

Stakeholders to involve

| Organisations to be involved | Named Contacts | Contact details | Comments |  |
| --- | --- | --- | --- | --- |
| MCC | Jill Thompson or Joanne Royle |  |  |  |
| Sporting Personality |  | UHSM Comms? |  | MUFC / Basket Ball / Athletics |
| Fire Service |  | From Ray Keelan |  |  |
| Police |  |  |  |  |
| NWAS | Julie Butterworth | julie.butterworth@nwas.nhs.uk |  |  |
| MMHSCT | Trish Dwyer | Trish.Dwyer@mhsc.nhs.uk | 0161 882 1000 |  |
| Age Friendly Manchester - MCC | Paul McGarry | p.mcgarry@manchester.gov.uk 0161 234 3503 |  |  |
| Age UK | Debbie Meek | Debbie.Meek@ageukmanchester.org.uk |  |  |
| Community Explorers | Claire Tomkinson | C.Tomkinson@southwayhousing.co.uk |  |  |
| Manchester Carers Forum | Dave Williams | dave@manchestercarersforum.org.uk |  |  |
| North West - Stroke Association" | Chris Larkin - Regional Director | Chris.Larkin@stroke.org.uk | 0161 745 8222 | Living Well week Frailty week |
| Intelesant Frailty tool | Louise Rogerson | louise@intelesant.com | 07736 039817 |  |
| Wythenshawe Forum | Jane Ayrton | j.ayrton@mancehster.gov.uk or 227 3770 | Willing to participate with grand day out |  |
| Manchester LPC (Community Pharmacy) | Claire | Claire@cpgm.org.uk or | 07841 830706 |  |
| Community Alarms | Donna Connors | Donna.Connors@Manchester.gov.uk 0161 277 1838 | Willing to participate in Frailty Week and Gen Comm Services week |  |
| Independent Life Solutions – (Assistive technology) | Paul Grimsley Frank Hibbard | 07540 342616 07711 046086 | Willing to participate |  |

Questions for Communications team

| W/c | Question | Subject |  |  |
| --- | --- | --- | --- | --- |
| 29 September 2015 | Can we have a celebrity for photo opportunities | Living Well |  |  |
| 05 October 2015 | Can we have a celebrity for photo opportunities | Mental Health |  |  |
| 12 October 2015 | Can we have a celebrity for photo opportunities | Frailty |  |  |
|  | Can we dedicate Manchester Weekly News column to the 4 weekly event? | General |  |  |